|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Task Mode** | **WBS** | **Task Name** | **Duration** | **Start** | **Finish** | **Predecessors** | **Resource Names** |
| Auto Scheduled | 1 | Get new schedule | 5 mins | Mon 19-09-02 | Mon 19-09-02 |  | Sudha Sanan |
| **Auto Scheduled** | **2** | **Word** | **0.13 days** | **Mon 19-09-02** | **Mon 19-09-02** |  |  |
| **Auto Scheduled** | **A** | **Read Word textbook and work through projects** | **0.13 days** | **Mon 19-09-02** | **Mon 19-09-02** |  | **Kyle Smith,Sudha Sanan** |
| Auto Scheduled | a | Review end-of-chapter exercises | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | Kyle Smith |
| Auto Scheduled | b | Check all work | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | Kyle Smith |
| **Auto Scheduled** | **3** | **Excel** | **0.13 days** | **Mon 19-09-02** | **Mon 19-09-02** |  |  |
| **Auto Scheduled** | **A** | **Read Excel textbook and work through projects** | **0.13 days** | **Mon 19-09-02** | **Mon 19-09-02** |  | **Kyle Smith,Sudha Sanan** |
| Auto Scheduled | a | Review end-of-chapter exercises | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | Kyle Smith |
| Auto Scheduled | b | Check all work | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | Kyle Smith |
| **Auto Scheduled** | **4** | **PowerPoint** | **0.13 days** | **Mon 19-09-02** | **Mon 19-09-02** |  |  |
| **Auto Scheduled** | **A** | **Read PowerPoint textbook and work through projects** | **0.13 days** | **Mon 19-09-02** | **Mon 19-09-02** |  | **Kyle Smith,Sudha Sanan** |
| Auto Scheduled | a | Review end-of-chapter exercises | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | Kyle Smith |
| Auto Scheduled | b | Check all work | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | Kyle Smith |
| Auto Scheduled | 5 | Verify students and courses | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | William Cook |
| Auto Scheduled | 6 | Make necessary corrections to student list | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | William Cook |
| Auto Scheduled | 7 | Create labels with student name and course name | 2 hrs | Mon 19-09-02 | Mon 19-09-02 |  | William Cook |
| Auto Scheduled | 8 | Copy/print course materials | 3 hrs | Mon 19-09-02 | Mon 19-09-02 |  | Sudha Sanan |
| Auto Scheduled | 9 | Set color-coded folders | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | John Walker |
| Auto Scheduled | 10 | Add labels and course materials to folders | 2 hrs | Mon 19-09-02 | Mon 19-09-02 |  | John Walker |
| Auto Scheduled | 11 | Get books from bookstore | 2 hrs | Mon 19-09-02 | Mon 19-09-02 |  | Sudha Sanan |
| Auto Scheduled | 12 | Verify books and course material folders for each student | 2 hrs | Mon 19-09-02 | Mon 19-09-02 |  | David Grant |
| Auto Scheduled | 13 | Verify attendance sheets with books and course materials | 2 hrs | Mon 19-09-02 | Mon 19-09-02 |  | David Grant |
| Auto Scheduled | 14 | First Day | 0 days | Tue 19-09-03 | Tue 19-09-03 |  | Sudha Sanan |