## Sheet1
Task Mode | WBS | Task Name | Duration | Start | Finish | Predecessors | Resource Names
Auto Scheduled | 1 | Get new schedule | 5 mins | Mon 19-09-02 | Mon 19-09-02 |  | Sudha Sanan
Auto Scheduled | 2 | Word | 0.13 days | Mon 19-09-02 | Mon 19-09-02
Auto Scheduled | A | Read Word textbook and work through projects | 0.13 days | Mon 19-09-02 | Mon 19-09-02 |  | Kyle Smith,Sudha Sanan
Auto Scheduled | a | Review end-of-chapter exercises | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | Kyle Smith
Auto Scheduled | b | Check all work | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | Kyle Smith
Auto Scheduled | 3 | Excel | 0.13 days | Mon 19-09-02 | Mon 19-09-02
Auto Scheduled | A | Read Excel textbook and work through projects | 0.13 days | Mon 19-09-02 | Mon 19-09-02 |  | Kyle Smith,Sudha Sanan
Auto Scheduled | a | Review end-of-chapter exercises | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | Kyle Smith
Auto Scheduled | b | Check all work | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | Kyle Smith
Auto Scheduled | 4 | PowerPoint | 0.13 days | Mon 19-09-02 | Mon 19-09-02
Auto Scheduled | A | Read PowerPoint textbook and work through projects | 0.13 days | Mon 19-09-02 | Mon 19-09-02 |  | Kyle Smith,Sudha Sanan
Auto Scheduled | a | Review end-of-chapter exercises | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | Kyle Smith
Auto Scheduled | b | Check all work | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | Kyle Smith
Auto Scheduled | 5 | Verify students and courses | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | William Cook
Auto Scheduled | 6 | Make necessary corrections to student list | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | William Cook
Auto Scheduled | 7 | Create labels with student name and course name | 2 hrs | Mon 19-09-02 | Mon 19-09-02 |  | William Cook
Auto Scheduled | 8 | Copy/print course materials | 3 hrs | Mon 19-09-02 | Mon 19-09-02 |  | Sudha Sanan
Auto Scheduled | 9 | Set color-coded folders | 1 hr | Mon 19-09-02 | Mon 19-09-02 |  | John Walker
Auto Scheduled | 10 | Add labels and course materials to folders | 2 hrs | Mon 19-09-02 | Mon 19-09-02 |  | John Walker
Auto Scheduled | 11 | Get books from bookstore | 2 hrs | Mon 19-09-02 | Mon 19-09-02 |  | Sudha Sanan
Auto Scheduled | 12 | Verify books and course material folders for each student | 2 hrs | Mon 19-09-02 | Mon 19-09-02 |  | David Grant
Auto Scheduled | 13 | Verify attendance sheets with books and course materials | 2 hrs | Mon 19-09-02 | Mon 19-09-02 |  | David Grant
Auto Scheduled | 14 | First Day | 0 days | Tue 19-09-03 | Tue 19-09-03 |  | Sudha Sanan